## Agile Project Charter
AGILE PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME
PROJECT CHAMPION
PROJECT SPONSOR
PROJECT MANAGER
STAKEHOLDERS
EXPECTED START DATE
EXPECTED COMPLETION DATE
PROJECT DETAILS
EXECUTIVE SUMMARY
AUTHORIZATION
OBJECTIVES
EXPECTED BENEFITS
SCOPE
MILESTONES
SUCCESS METRICS
ESTIMATED COST & RESOURCES
DATE
CLICK HERE TO CREATE IN SMARTSHEET

## Sheet1
AGILE PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | EvolutionCo Digital Project Management & Client CRM System
PROJECT CHAMPION | CEO Mr. Rajiv Sharma
PROJECT SPONSOR | COO of EvolutionCo
PROJECT MANAGER | Ms. Anjali Mehta
STAKEHOLDERS | Satyam Pandey
EXPECTED START DATE | 2025-10-22
EXPECTED COMPLETION DATE | 2026-01-12
PROJECT DETAILS
EXECUTIVE SUMMARY | EvolutionCo is facing inefficiencies in client management and project tracking due to manual processes using spreadsheets and emails. This project aims to develop an internal Digital Project Management & Client CRM System to streamline workflows, improve visibility, and enhance collaboration across Sales, Project Management, and Finance teams.
AUTHORIZATION | This project is authorized by the CEO of EvolutionCo, with [Your Name] assigned as Business Analyst and Alex as Project Manager to oversee development and delivery.
OBJECTIVES | 1. Digitize client onboarding, proposal tracking, task allocation, and invoicing workflows. 2. Provide real-time visibility into project health, resource utilization, and profitability via dashboards. 3. Reduce manual effort and communication redundancies by 50%.
EXPECTED BENEFITS | 1. 50% reduction in invoicing time, improving cash flow. 2. 80% visibility into task completion, enhancing project delivery. 3. Improved client satisfaction through streamlined communication and analytics for upselling.
SCOPE | In-Scope: Client onboarding module, proposal and project pipeline, task allocation and tracking, invoicing and payment monitoring, KPI dashboard. Out-of-Scope: Third-party integrations (e.g., Google Workspace, accounting software), HR or payroll functionalities, marketing automation, client feedback module (deferred to Phase 2).
MILESTONES | Week 1 (Oct 27, 2025): Project Charter and Stakeholder Register approved. Week 4 (Nov 17, 2025): BRD finalized. Week 6 (Dec 1, 2025): FRD and wireframes completed. Week 10 (Dec 29, 2025): Testing and UAT completed. Week 12 (Jan 12, 2026): MVP deployment and training.
SUCCESS METRICS | 50% reduction in invoicing processing time. 80% visibility into task completion rates across projects. 90% user adoption rate among Sales, PMs, and Finance teams post-training.
ESTIMATED COST & RESOURCES | Budget: ~$50,000 for internal development (no external vendors). Resources: 1 BA ([Your Name]), 1 PM (Alex), 1 Tech Lead (Jordan), 2-3 Developers, 1 QA, 1 UI/UX Designer, internal servers for deployment.
DATE | October 21, 2025

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.